## Instructions
Better Health Outcomes for North Coast Communities
Tool for Reporting Progress on the memorandum of understanding
Instructions for quarterly reporting
There are four tables: 1. Reporting - Schedule of works, 2. Mitigation
Reporting - Schedule of Works
Field | Instructions | Detail
Quarter status | Use drop-down | The responsible party updates the status of the action at the end of the reportable quarter Options: Progressing On track/Complete Off track.
Quarter status update | Enter text | The responsible party enters a brief summary of relevant information - this may be a description of what has taken place or the actions being taken to correct the course of the action if it is delayed.
Mitigation
Field | Instructions | Detail
Activity | Nil | This is a full list of activities
Lead | Nil | The responsible party
Timeline | Nil | The date of completion
Reporting date | Nil | This is automatically highlighted in orange if the action is marked as "Off track" in the Reporting - Schedule of works table.
Mitigation of activities yr qtr that are off track | If indicated by an orange box enter detail | The responsible party provides an explanation, detailing the mitigation plan
Completion register
Field | Instructions | Detail
HNC complete | Use drop-down | The responsible party indicates completion of all actions the responsible party is responsible for in the reportable quarter.
NNSW LHD complete
MNC LHD complete
Changes log
Field | Instructions | Detail
Changes to be made | Enter text | Changes that any party want to request be made to the Schedule or reporting template.
Party requesting change (drop-down) | Use drop-down | Select the party requesting the change.

## Reporting - Schedule of Works
Better Health Outcomes for North Coast Communities Memorandum of Understanding
Schedule of Works | [5 empty] | Jan - Mar 2024 |  | Apr - Jun 2024 |  | Jul - Sep 2025 |  | Oct - Dec 2025 |  | Jan - Mar 2025 |  | Apr - Jun 2025 |  | Jul - Sep 2026 |  | Oct - Dec 2026 |  | Jan - Mar 2026 |  | Apr - Jun 2026 |  | Jul - Sep 2027 |  | Oct - Dec 2027 |  | Jan - Mar 2027 |  | Apr - Jun 2027 |  | Jul - Sep 2028 |  | Oct - Dec 2028
Activity area | Activity_Number | Activity type | Activity | Lead | Timeline | 2024 Q3 status | 2024 Q3 Status update | 2024 Q4 status | 2024 Q4 Status update | 2025 Q1 status | 2025 Q1 Status update | 2025 Q2 status | 2025 Q2 Status update | 2025 Q3 status | 2025 Q3 Status update | 2025 Q4 status | 2025 Q4 Status update | 2026 Q1 status | 2026 Q1 Status update | 2026 Q2 status | 2026 Q2 Status update | 2026 Q3 status | 2026 Q3 Status update | 2026 Q4 status | 2026 Q4 Status update | 2027 Q1 status | 2027 Q1 Status update | 2027 Q2 status | 2027 Q2 Status update | 2027 Q3 status | 2027 Q3 Status update | 2027 Q4 status | 2027 Q4 Status update | 2028 Q1 status | 2028 Q1 Status update | 2028 Q2 status | 2028 Q2 Status update
Services planning and commissioning | 1 | Joint planning | Scope the establishment of a joint population health needs assessment | HNC | 2025-06-01 | Progressing | Not due to start yet
Services planning and commissioning | 1 | Joint planning | Explore shared planning resources | HNC | 2026-06-01 | Progressing | Not due to start yet
Services planning and commissioning | 1 | Joint planning | Establish data sharing agreements | HNC | 2026-06-01 | Progressing | Not due to start yet
Services planning and commissioning | 1 | Joint planning | Conduct joint population health needs assessment | HNC | 2027-12-01 | Progressing | Not due to start yet
Services planning and commissioning | 1 | Joint planning | Identify key priorities – i.e. overrepresented conditions, unwarranted clinical variation | HNC | 2028-03-01 | Progressing | Not due to start yet
Services planning and commissioning | 1 | Joint planning | Co-design care modalities and pathways | HNC | 2028-06-01 | Progressing | Not due to start yet
Services planning and commissioning | 1 | Joint planning | Scope collaborative commissioning opportunities to address priority areas and populations | HNC | 2028-12-01 | Progressing | Not due to start yet
Services planning and commissioning | 2 | Value Based Health Care | Develop a framework for VBHC across the region | HNC | 2025-06-01 | Progressing
Services planning and commissioning | 2 | Value Based Health Care | Define priority areas amenable to VBHC approaches across the patient journey from community and primary care through to sub-acute and acute care | HNC | 2025-06-01 | Progressing | Initiatives underway: Statewide Diabetes Management project Chronic Wound Care Health Pathways project – LBVC Direct Access Colonoscopy project- LBVC
Services planning and commissioning | 2 | Value Based Health Care | Develop implementation plan for VBHC joint projects | HNC | 2025-06-01 | Progressing
Mental Health and AOD | 3 | Joint regional Mental Health, Suicide Prevention and AOD Plan | Establish governance structure | HNC | 2023-08-01 | On track/Complete
Mental Health and AOD | 3 | Joint regional Mental Health, Suicide Prevention and AOD Plan | Develop project plan and scope of works | HNC | 2023-09-01 | On track/Complete
Mental Health and AOD | 3 | Joint regional Mental Health, Suicide Prevention and AOD Plan | Analyse service level agreements, funding schedules for PHN and LHD and national frameworks and evaluations, to identify collective priorities or areas of focus. | HNC | 2023-10-01 | On track/Complete
Mental Health and AOD | 3 | Joint regional Mental Health, Suicide Prevention and AOD Plan | Develop joint regional plan | HNC | 2023-11-01 | On track/Complete
Mental Health and AOD | 3 | Joint regional Mental Health, Suicide Prevention and AOD Plan | Joint regional plan is endorsed by LHDs and PHN | HNC | 2024-02-01 | On track/Complete
Mental Health and AOD | 3 | Joint regional Mental Health, Suicide Prevention and AOD Plan | Joint regional plan submitted to the Department of Health and Ageing and NSW Health Ministry of Health | HNC | 2024-03-01 | On track/Complete | Mental Health, Suicide Prevention and AOD Plan successfully submitted to the Department of Health and Aged Care and the NSW Ministry of Health, 7 March 2024.
Mental Health and AOD | 3 | Joint regional Mental Health, Suicide Prevention and AOD Plan | Joint regional plan implementation plans developed | HNC | 2024-06-01 | On track/Complete
Mental Health and AOD | 3 | Joint regional Mental Health, Suicide Prevention and AOD Plan | Reference group established | HNC | 2024-06-01 | On track/Complete
Mental Health and AOD | 3 | Joint regional Mental Health, Suicide Prevention and AOD Plan | Plan performance monitored and evaluated | HNC | Ongoing | On track/Complete
Ageing Well | 4 | Healthy ageing and ageing well | Establish integrated aged care model – including enhancing the community’s access to Residential Aged Care Homes | HNC | 2024-12-01 | Progressing | Not due to start yet
Ageing Well | 4 | Healthy ageing and ageing well | Enhance end of life care planning across acute and primary health care | MNC LHD, NNSW LHD | 2024-12-01 | On track/Complete | Liaison between HNC’s Greater Choice and the LHD Palliative Care teams is underway. Collaboration took place in late 2023 to coordinate the roll out of the Voluntary Assisted Dying.
Ageing Well | 4 | Healthy ageing and ageing well | Conduct joint advocacy for the enhanced provision of specialist dementia Residential Aged Care Home beds | HNC, MNC LHD, NNSW LHD | 2024-12-01 | Progressing | Not due to start yet
Aboriginal and Torres Strait Islander Health | 5 | Mid North Coast Accord | Mid North Coast Accord | MNC LHD | Ongoing | On track/Complete | Last meeting held 26 March 2024.
Aboriginal and Torres Strait Islander Health | 6 | Northern NSW Aboriginal Partnerships Forum | Northern NSW Aboriginal Partnerships Forum | NNSW LHD | Ongoing | On track/Complete | Last meeting scheduled for 18 March 2024 postponed due to extensive apologies.
Aboriginal and Torres Strait Islander Health | 7 | Child and maternal health | Conduct review of AMIHS demand | NNSW LHD | 2025-06-01 | Progressing | Not due to start yet
Health Care Access | 8 | Service navigation and wayfinding for consumers | Develop and launch a consumer campaign to improve health service information and navigation | HNC, NNSW LHD | 2024-12-01 | Progressing | HNC has begun developing resources
Health Care Access | 8 | Service navigation and wayfinding for consumers | Embed HealthDirect as the NSW single front door | HNC | 2025-06-01 | On track/Complete | MNC Virtual Care intake transitioning to healthdirect in the coming months. Negotiations underway with DoHAC, NSW MoH and healthdirect to support the transition of the North Coast Health Connect service to healthdirect by June 2025.
Health Care Access | 8 | Service navigation and wayfinding for consumers | Continue the NNSW Health Literacy project which seeks to improve access to health care and the community’s ability to act on health information and services. | HNC, NNSW LHD | Ongoing | On track/Complete | Project is continuing strongly with staffing in place and high engagement amongst health professionals of resources and support provided.
Health Care Access | 9 | Urgent Care | Medicare Urgent Care Clinic - Lismore | HNC | Ongoing
Health Care Access | 9 | Urgent Care | Medicare Urgent Care Clinic - Coffs Harbour | HNC | Ongoing | On track/Complete | Fully operational 8am – 8pm seven days per week. 8% clients are Aboriginal. Between 16 – 36 presentations per day. 1,596 presentations since clinic opened in November 2023.
Health Care Access | 9 | Urgent Care | Medicare Urgent Care Clinic – Joint regional advocacy for a Grafton clinic | HNC, NNSW LHD | 2024-06-01 | On track/Complete | Fully operational 8am – 8pm seven days per week. 18% clients are Aboriginal. Between 12 – 32 presentations per day. 1,751 presentations since clinic opened in November 2023.
Health Care Access | 9 | Urgent Care | Medical Urgent Care Clinic – Joint regional advocacy for a Port Macquarie clinic | HNC, MNC LHD | 2024-06-01 | Progressing | Hasn't started yet.
Health Care Access | 9 | Urgent Care | Tweed Urgent Care Service | NNSW LHD | 2024-06-01 | Progressing | The opening of the Tweed Hospital has been the top priority. As such, there has been a delay in the progress of the urgent care service.
Health Care Access | 9 | Urgent Care | Mid North Coast Virtual Care | MNC LHD | Ongoing | On track/Complete | Ongoing. Intake will transition to healthdirect in the coming months.
Health Care Access | 9 | Urgent Care | North Coast Health Connect distributed model of urgent care GP and pharmacy appointments | HNC | Ongoing | On track/Complete | 12,400 calls since region-wide establishment in May 2023. Majority of calls from Port Macquarie (2,155). 1,241 GP urgent care, 793 GP telehealth and 66 pharmacy appointments brokered through service.
Health Care Access | 10 | HealthPathways | Maintenance of 700+ Mid and North Coast pathways with a view to rationalising as appropriate | HNC | Ongoing | On track/Complete | Maintenance of pathways ongoing.
Health Care Access | 10 | HealthPathways | Scope automation of the collection and publishing of service information on HealthPathways | HNC | 2025-06-01 | Progressing | Not due to start yet
Health Care Access | 11 | Undertake analysis of avoidable hospital admissions | Acute conditions | MNC LHD, NNSW LHD | 2024-12-01 | Progressing | Not due to start yet
Health Care Access | 11 | Undertake analysis of avoidable hospital admissions | Chronic conditions | MNC LHD, NNSW LHD | 2025-01-01 | Progressing | Not due to start yet
Health Care Access | 11 | Undertake analysis of avoidable hospital admissions | Availability of general practice and allied health | MNC LHD, NNSW LHD | 2025-02-01 | Progressing | Not due to start yet
Health Care Access | 11 | Undertake analysis of avoidable hospital admissions | Availability of public medical specialist outpatients services | MNC LHD, NNSW LHD | 2025-03-01 | Progressing | Not due to start yet
Disaster and Emergency Management | 12 | Prevention | Fund community capacity and resilience building activities | HNC | 2024-12-01 | On track/Complete | HNC current has open the third round of Community Wellbeing and Resilience grants.
Disaster and Emergency Management | 12 | Preparedness | Establish joint whole of system working group to plan and prepare for disasters, with primary health care embedded in response plan/s | HNC | 2024-06-01 | On track/Complete | Meetings held between HNC and NNSW LHD to progress. Engagement with MNC LHD still to take place.
Disaster and Emergency Management | 12 | Preparedness | Annual scenario planning between LHD, HNC and primary care, inclusive of LHD incorporation of HNC disaster response framework in regional health plan/s | MNC LHD, NNSW LHD | Annually | On track/Complete | ‘Exercise Atlantis’ scenario planning exercise held between HNC, NNSW LHD, SES, Police, DCJ and Ambulance on 8 February 2024. Scenario to be planned in MNC.
Disaster and Emergency Management | 12 | Response | Joint response efforts led by LHDs, supported by HNC | MNC LHD, NNSW LHD | As required | Progressing | Not currently required.
Disaster and Emergency Management | 12 | Recovery | Implementation of agreed activities as required after disasters | HNC | As required | On track/Complete | NNSW 2022 flood recovery supports in place, although some services have needed to be decommissioned. Funding has been extended until December 2025 for the four Safe Haven sites in Northern NSW.
Population and Public Health | 13 | Population Health | Develop and implement a joint population health campaign promoting influenza and COVID-19 vaccination | HNC | March to June annually | On track/Complete | Planning complete. Campaign to be jointly launched from 8 April onwards.
Population and Public Health | 13 | Population Health | Undertake targeted activities to increase influenza vaccination for people living in Residential Aged Care Homes | HNC | Ongoing | Progressing | To be undertaken by HNC’s Healthy Ageing Team and the North Coast Public Health Unit.
Population and Public Health | 13 | Population Health | Undertake targeted activities to increase vaccination for children and other priority populations | HNC, MNC LHD, NNSW LHD | Ongoing | Progressing | To be undertaken by HNC’s Population Health Team and the North Coast Public Health Unit.
Population and Public Health | 14 | Public Health | Joint monitoring of surveillance reports | MNC LHD, NNSW LHD | Ongoing | On track/Complete | North Coast Public Health Unit Respiratory surveillance reports now shared with HNC’s Population Health Team.
Population and Public Health | 14 | Public Health | Joint identification and action on emerging public health risks | MNC LHD, NNSW LHD | Ongoing | On track/Complete | STI and Sexual Health Education for GPs held in February 2024 across the region, in response to increased rates of syphilis in the region.
Population and Public Health | 14 | Public Health | Undertake collaborative approaches to reducing communicable diseases and environmental health risks | MNC LHD, NNSW LHD | Ongoing | Progressing | No activities currently.
Workforce retention and capacity building | 15 | Run interdisciplinary clinical societies in eight regions (2-3 per annum per region) to build workforce capacity and integration between acute and primary health care services | Run interdisciplinary clinical societies in eight regions (2-3 per annum per region) to build workforce capacity and integration between acute and primary health care services | HNC | Ongoing | On track/Complete | HNC’s education calendar includes all eight sub-regions having regular education nights – acute and primary health care clinicians attend these events.
Workforce retention and capacity building | 16 | Centre for Health Care Knowledge and Innovation (CHKI) | Relaunch the Centre to provide a platform to bring big and bold ideas to the region and showcase innovation | HNC | 2024-06-01 | On track/Complete | HNC is relaunching CHKI in 2024. Both LHDs have opted to not be involved currently.
Workforce retention and capacity building | 17 | Establish trials of innovative workforce models to increase access to general practice in at-risk rural communities | Clarence Valley | HNC, NNSW LHD | 2026-06-01 | Progressing | NSW MoH is rolling out the GP Single Employer Model in restricted locations across the region. Further work to be undertaken to explore other innovative workforce models.
Workforce retention and capacity building | 17 | Establish trials of innovative workforce models to increase access to general practice in at-risk rural communities | Richmond Valley | HNC, NNSW LHD | 2026-07-01 | Progressing
Workforce retention and capacity building | 17 | Establish trials of innovative workforce models to increase access to general practice in at-risk rural communities | Kempsey | HNC, MNC LHD | 2026-08-01 | Progressing
Workforce retention and capacity building | 17 | Establish trials of innovative workforce models to increase access to general practice in at-risk rural communities | Bellingen/Nambucca | HNC, MNC LHD | 2026-09-01 | Progressing

## Mitigation
Better Health Outcomes for North Coast Communities Memorandum of Understanding
Mitigation of activities off track
Orange indicates this activity is OFF TRACK - details of mitigation are required.
Green indicates the activity is OFF TRACK and details of mitigation have been provided.
Activity | Lead | Timeline | 2024 Q3 | Mitigation of 2024 Q3 activities that are off track | 2024 Q4 | Mitigation of 2024 Q4 activities that are off track | 2025 Q1 | Mitigation of 2025 Q1 activities that are off track | 2025 Q2 | Mitigation of 2025 Q2 activities that are off track | 2025 Q3 | Mitigation of 2025 Q3 activities that are off track | 2025 Q4 | Mitigation of 2025 Q4 activities that are off track | 2026 Q1 | Mitigation of 2026 Q1 activities that are off track
Scope the establishment of a joint population health needs assessment | HNC | 2025-06-01
Explore shared planning resources | HNC | 2026-06-01
Establish data sharing agreements | HNC | 2026-06-01
Conduct joint population health needs assessment | HNC | 2027-12-01
Identify key priorities – i.e. overrepresented conditions, unwarranted clinical variation | HNC | 2028-03-01
Co-design care modalities and pathways | HNC | 2028-06-01
Scope collaborative commissioning opportunities to address priority areas and populations | HNC | 2028-12-01
Develop a framework for VBHC across the region | HNC | 2025-06-01
Define priority areas amenable to VBHC approaches across the patient journey from community and primary care through to sub-acute and acute care | HNC | 2025-06-01
Develop implementation plan for VBHC joint projects | HNC | 2025-06-01
Establish governance structure | HNC | 2023-08-01
Develop project plan and scope of works | HNC | 2023-09-01
Analyse service level agreements, funding schedules for PHN and LHD and national frameworks and evaluations, to identify collective priorities or areas of focus. | HNC | 2023-10-01
Develop joint regional plan | HNC | 2023-11-01
Joint regional plan is endorsed by LHDs and PHN | HNC | 2024-02-01
Joint regional plan submitted to the Department of Health and Ageing and NSW Health Ministry of Health | HNC | 2024-03-01
Joint regional plan implementation plans developed | HNC | 2024-06-01
Reference group established | HNC | 2024-06-01
Plan performance monitored and evaluated | HNC | Ongoing
Establish integrated aged care model – including enhancing the community’s access to Residential Aged Care Homes | HNC | 2024-12-01
Enhance end of life care planning across acute and primary health care | MNC LHD, NNSW LHD | 2024-12-01
Conduct joint advocacy for the enhanced provision of specialist dementia Residential Aged Care Home beds | HNC, MNC LHD, NNSW LHD | 2024-12-01
Mid North Coast Accord | MNC LHD | Ongoing
Northern NSW Aboriginal Partnerships Forum | NNSW LHD | Ongoing
Conduct review of AMIHS demand | NNSW LHD | 2025-06-01
Develop and launch a consumer campaign to improve health service information and navigation | HNC, NNSW LHD | 2024-12-01
Embed HealthDirect as the NSW single front door | HNC | 2025-06-01
Continue the NNSW Health Literacy project which seeks to improve access to health care and the community’s ability to act on health information and services. | HNC, NNSW LHD | Ongoing
Medicare Urgent Care Clinic - Lismore | HNC | Ongoing
Medicare Urgent Care Clinic - Coffs Harbour | HNC | Ongoing
Medicare Urgent Care Clinic – Joint regional advocacy for a Grafton clinic | HNC, NNSW LHD | 2024-06-01
Medical Urgent Care Clinic – Joint regional advocacy for a Port Macquarie clinic | HNC, MNC LHD | 2024-06-01
Tweed Urgent Care Service | NNSW LHD | 2024-06-01
Mid North Coast Virtual Care | MNC LHD | Ongoing
North Coast Health Connect distributed model of urgent care GP and pharmacy appointments | HNC | Ongoing
Maintenance of 700+ Mid and North Coast pathways with a view to rationalising as appropriate | HNC | Ongoing
Scope automation of the collection and publishing of service information on HealthPathways | HNC | 2025-06-01
Acute conditions | MNC LHD, NNSW LHD | 2024-12-01
Chronic conditions | MNC LHD, NNSW LHD | 2025-01-01
Availability of general practice and allied health | MNC LHD, NNSW LHD | 2025-02-01
Availability of public medical specialist outpatients services | MNC LHD, NNSW LHD | 2025-03-01
Fund community capacity and resilience building activities | HNC | 2024-12-01
Establish joint whole of system working group to plan and prepare for disasters, with primary health care embedded in response plan/s | HNC | 2024-06-01
Annual scenario planning between LHD, HNC and primary care, inclusive of LHD incorporation of HNC disaster response framework in regional health plan/s | MNC LHD, NNSW LHD | Annually
Joint response efforts led by LHDs, supported by HNC | MNC LHD, NNSW LHD | As required
Implementation of agreed activities as required after disasters | HNC | As required
Develop and implement a joint population health campaign promoting influenza and COVID-19 vaccination | HNC | March to June annually
Undertake targeted activities to increase influenza vaccination for people living in Residential Aged Care Homes | HNC | Ongoing
Undertake targeted activities to increase vaccination for children and other priority populations | HNC, MNC LHD, NNSW LHD | Ongoing
Joint monitoring of surveillance reports | MNC LHD, NNSW LHD | Ongoing
Joint identification and action on emerging public health risks | MNC LHD, NNSW LHD | Ongoing
Undertake collaborative approaches to reducing communicable diseases and environmental health risks | MNC LHD, NNSW LHD | Ongoing
Run interdisciplinary clinical societies in eight regions (2-3 per annum per region) to build workforce capacity and integration between acute and primary health care services | HNC | Ongoing
Relaunch the Centre to provide a platform to bring big and bold ideas to the region and showcase innovation | HNC | 2024-06-01
Clarence Valley | HNC, NNSW LHD | 2026-06-01
Richmond Valley | HNC, NNSW LHD | 2026-07-01
Kempsey | HNC, MNC LHD | 2026-08-01
Bellingen/Nambucca | HNC, MNC LHD | 2026-09-01

## Completion register
Better Health Outcomes for North Coast Communities Memorandum of Understanding
Completion register
Financial Year | Field heading | Period month | Year | Period mth yr | Quarter | Type | Field calculated | HNC Complete | NNSW LHD complete | MNC LHD Complete
2022-23 | 2023 Q3 status | Jan - Mar | 2023 | Jan - Mar 2023 | Q3 | Status | 2023 Q3 Status | P | P | P
2022-23 | 2023 Q3 Status update | Jan - Mar | 2023 | Jan - Mar 2023 | Q3 | Status update | 2023 Q3 Status update | P | P | P
2022-23 | 2023 Q4 status | Apr - Jun | 2023 | Apr - Jun 2023 | Q4 | Status | 2023 Q4 Status
2022-23 | 2023 Q4 Status update | Apr - Jun | 2023 | Apr - Jun 2023 | Q4 | Status update | 2023 Q4 Status update
2023-24 | 2023 Q1 status | Jul - Sep | 2023 | Jul - Sep 2023 | Q1 | Status | 2023 Q1 Status
2023-24 | 2023 Q1 Status update | Jul - Sep | 2023 | Jul - Sep 2023 | Q1 | Status update | 2023 Q1 Status update
2023-24 | 2023 Q2 status | Oct - Dec | 2023 | Oct - Dec 2023 | Q2 | Status | 2023 Q2 Status
2023-24 | 2023 Q2 Status update | Oct - Dec | 2023 | Oct - Dec 2023 | Q2 | Status update | 2023 Q2 Status update
2023-24 | 2024 Q3 status | Jan - Mar | 2024 | Jan - Mar 2024 | Q3 | Status | 2024 Q3 Status
2023-24 | 2024 Q3 Status update | Jan - Mar | 2024 | Jan - Mar 2024 | Q3 | Status update | 2024 Q3 Status update
2023-24 | 2024 Q4 status | Apr - Jun | 2024 | Apr - Jun 2024 | Q4 | Status | 2024 Q4 Status
2023-24 | 2024 Q4 Status update | Apr - Jun | 2024 | Apr - Jun 2024 | Q4 | Status update | 2024 Q4 Status update
2024-25 | 2025 Q1 status | Jul - Sep | 2025 | Jul - Sep 2025 | Q1 | Status | 2025 Q1 Status
2024-25 | 2025 Q1 Status update | Jul - Sep | 2025 | Jul - Sep 2025 | Q1 | Status update | 2025 Q1 Status update
2024-25 | 2025 Q2 status | Oct - Dec | 2025 | Oct - Dec 2025 | Q2 | Status | 2025 Q2 Status
2024-25 | 2025 Q2 Status update | Oct - Dec | 2025 | Oct - Dec 2025 | Q2 | Status update | 2025 Q2 Status update
2024-25 | 2025 Q3 status | Jan - Mar | 2025 | Jan - Mar 2025 | Q3 | Status | 2025 Q3 Status
2024-25 | 2025 Q3 Status update | Jan - Mar | 2025 | Jan - Mar 2025 | Q3 | Status update | 2025 Q3 Status update
2024-25 | 2025 Q4 status | Apr - Jun | 2025 | Apr - Jun 2025 | Q4 | Status | 2025 Q4 Status
2024-25 | 2025 Q4 Status update | Apr - Jun | 2025 | Apr - Jun 2025 | Q4 | Status update | 2025 Q4 Status update
2025-26 | 2026 Q1 status | Jul - Sep | 2026 | Jul - Sep 2026 | Q1 | Status | 2026 Q1 Status
2025-26 | 2026 Q1 Status update | Jul - Sep | 2026 | Jul - Sep 2026 | Q1 | Status update | 2026 Q1 Status update
2025-26 | 2026 Q2 status | Oct - Dec | 2026 | Oct - Dec 2026 | Q2 | Status | 2026 Q2 Status
2025-26 | 2026 Q2 Status update | Oct - Dec | 2026 | Oct - Dec 2026 | Q2 | Status update | 2026 Q2 Status update
2025-26 | 2026 Q3 status | Jan - Mar | 2026 | Jan - Mar 2026 | Q3 | Status | 2026 Q3 Status
2025-26 | 2026 Q3 Status update | Jan - Mar | 2026 | Jan - Mar 2026 | Q3 | Status update | 2026 Q3 Status update
2025-26 | 2026 Q4 status | Apr - Jun | 2026 | Apr - Jun 2026 | Q4 | Status | 2026 Q4 Status
2025-26 | 2026 Q4 Status update | Apr - Jun | 2026 | Apr - Jun 2026 | Q4 | Status update | 2026 Q4 Status update
2026-27 | 2027 Q1 status | Jul - Sep | 2027 | Jul - Sep 2027 | Q1 | Status | 2027 Q1 Status
2026-27 | 2027 Q1 Status update | Jul - Sep | 2027 | Jul - Sep 2027 | Q1 | Status update | 2027 Q1 Status update
2026-27 | 2027 Q2 status | Oct - Dec | 2027 | Oct - Dec 2027 | Q2 | Status | 2027 Q2 Status
2026-27 | 2027 Q2 Status update | Oct - Dec | 2027 | Oct - Dec 2027 | Q2 | Status update | 2027 Q2 Status update
2026-27 | 2027 Q3 status | Jan - Mar | 2027 | Jan - Mar 2027 | Q3 | Status | 2027 Q3 Status
2026-27 | 2027 Q3 Status update | Jan - Mar | 2027 | Jan - Mar 2027 | Q3 | Status update | 2027 Q3 Status update
2026-27 | 2027 Q4 status | Apr - Jun | 2027 | Apr - Jun 2027 | Q4 | Status | 2027 Q4 Status
2026-27 | 2027 Q4 Status update | Apr - Jun | 2027 | Apr - Jun 2027 | Q4 | Status update | 2027 Q4 Status update
2027-28 | 2028 Q1 status | Jul - Sep | 2028 | Jul - Sep 2028 | Q1 | Status | 2028 Q1 Status
2027-28 | 2028 Q1 Status update | Jul - Sep | 2028 | Jul - Sep 2028 | Q1 | Status update | 2028 Q1 Status update
2027-28 | 2028 Q2 status | Oct - Dec | 2028 | Oct - Dec 2028 | Q2 | Status | 2028 Q2 Status
2027-28 | 2028 Q2 Status update | Oct - Dec | 2028 | Oct - Dec 2028 | Q2 | Status update | 2028 Q2 Status update

## Changes log
Better Health Outcomes for North Coast Communities Memorandum of Understanding
Changes log
Change to be made | Party requesting change (drop-down) | Date change implemented

## Dropdowns
Progressing | HNC
Off track | NNSW LHD
On track/Complete | MNC LHD

## Sheet1
P